| Activity | Preceding activity | Time (weeks) |
| --- | --- | --- |
| 1. Requirements collection | - | 5 |
| 2. Screen design | 1 | 6 |
| 3. Reports design | 1 | 6 |
| 4. Database design | 2,3 | 2 |
| 5. user documentation | 4 | 5.5 |
| 6. programming | 4 | 5 |
| 7. Testing | 6 | 3 |
| 8. Installation | 5,7 | 1 |

- Draw a Network diagram for the activities

- Calculate the EST, LCT, and LST.

- Calculate the TFT for non-critical activities.

- Show the critical path.